# Checklist for Chapter 6 – Giving Dual Notice

| Date Completed | Item |
| --- | --- |
|  | 6 – Entire chapter reviewed before proceeding - Decision made on how to proceed |
|  | 6.1 – Considerations before proceeding - 6.1.1 – Rules and SONAR done - 6.1.2 – Allow time to complete steps - 6.1.3 – 60 days after Request for Comments published - 6.1.4 – With 18 months of new or revised rulemaking authority (if appliable) - 6.1.5 – Consideration for rules affecting farming operations - 6.1.6 – Counting time |
|  | 6.2 – Agency approval to give Notice obtained - If agency is a multi-member board, BD-NTC form used |
|  | 6.3 – Governor’s Office approval obtained - GOV-PRPS used |
|  | 6.3 – Consult with MMB - MMB-LTR used |
|  | 6.4 – Revisor’s Draft Approved for Publication obtained (with certificate signed by the Revisor) |
|  | 6.5 – Tentative hearing date and location set. CAH contacted. - 6.5.1 – Hearing date chosen. Factors considered: - 30-day comment period (minimum) - 10 additional days after end of comment period - CAH review time (5 working days) - Rules affecting farming operations (30 days additional notice and, if a public hearing, at least one in agricultural area – unless hearing is virtual) - State Register deadlines - Availability of key agency personnel - Give yourself enough time - 6.5.2 – Prehearing comment period considered - Optional for boards – BD-WKSHEET used - 6.5.3 – Location arranged; videoconference or virtual considered - 6.5.4 – CAH contacted |
|  | 6.6 – Dual Notice drafted - NTC-DL form used - 6.6.1 - Using CAH’s eComments website to collect comments considered - 6.6.2 - “Substantially different” rules considered |
|  | 6.6 – Dual Notice drafted - NTC-DL form used - 6.6.1 - Using CAH’s eComments website to collect comments considered - 6.6.2 - “Substantially different” rules considered |
|  | 6.7 – Additional Notice Plan developed |
|  | 6.8 – CAH contacted - 6.8.1 – ALJ assigned - 6.8.2 – Set up eComments (if using) - 6.8.3 – Letter to CAH - HR-RQST letter used for cover letter - Request approval of Additional Notice Plan (optional) - 6.8.4 - Request omission of full text of proposed rules from publication (rare) - 6.8.5 – eFile rule-related documents |
|  | 6.9 – Notice finalized - Notice signed and dated by: . |
|  | 6.10 – SONAR emailed to Legislative Reference Library - LRL used |
|  | 6.11 – Notice published in the State Register - State Register website used |
|  | 6.12 – Notice sent - CRT-LIST and CRT-MLNG used |
|  | 6.13 – Notice given per Additional Notice Plan - Actions documented and CRT-GNRC used |
|  | 6.14 – Notice given to Legislators - LEG used |
|  | 6.15 – Other applicable statute or rule requirements met |
|  | 6.16 – Comments tracked; lists maintained - comments on the rules, written or oral - hearing requests and hearing request withdrawals - requests for free copy of the rules - requests to be placed on the agency’s rulemaking mailing list - requests for notice of filing with the Secretary of State - requests for notice of submission to ALJ - COMMENT-TRACKER used |
|  | 6.17 – Proceed according to number of hearing requests - 6.17.3 - If 25 or more, hearing preparations made (Chapter 9) - Agency leadership, staff members, and agency AG (if using) notified - ALJ notified - Hearing room confirmed (if physical location used) - Hearing requestors notified. HTC-HR25 and CRT-HR25 used - 6.17.4 - If less than 25, hearing canceled and Chapter 8 used to adopt rules ** Hearing canceled at least 3 working days before hearing - Agency leadership, staff members, and agency AG (if using) notified - ALJ notified; ALJ-CNCL used - Hearing room canceled (if applicable) - If hearing withdrawals reduced number of hearing requests below 25, requestors notified. NTC-HRWD and CRT-HRWD used. - If fewer than 25 hearing requests (and agency did nothing to obtain withdrawals), requestors notified. NTC-CNCL used. |